## Sheet1
Sprint Plan for Leaf Application | Date Started | Date to be Completed by | Status
Create Communication Channels | 2023-10-31 | 2023-11-01 | Pass
Review Brief and take notes | 2023-10-31 | 2023-11-09 | Pass
Create Trello User Stories | 2023-11-06 | 2023-11-20 | Pass
Familarise ourselves with raw leaf detection code | 2023-11-15 | 2023-11-22 | Pass
Establish Project Framework | 2023-11-18 | 2023-12-02 | Pass
Create Figma Prototype Low-Fidelity | 2023-12-02 | 2023-12-15 | Pass
Create Android Studio Prototype High-Fidelity | 2023-12-15 | 2023-01-09 | Pass
Login Page API working | 2024-01-09 | 2024-01-16 | Pass
Discuss with Asiya Prototype changes | 2024-01-16 | 2024-01-23 | Pass
Improve the design of android studio | 2024-01-23 | 2024-01-30 | Pass
Add Java code to make settings work | 2024-01-30 | 2023-02-07 | Pass
Add java code to make the profile page work | 2024-01-30 | 2023-02-08 | Pass
Add camera functions | 2023-02-28 | 2023-03-03 | Pass
Add photo library storage functionality | 2023-03-03 | 2023-03-05 | Pass
Implement AI Code | 2024-03-05 | 2024-03-07 | Fail
Store the AI result | 2024-03-07 | 2024-03-10 | Fail
Display the AI result | 2024-03-10 | 2024-03-13 | Fail
User Testing | 2024-03-14 | 2024-04-14 | Pass